## Planned Actions
Latitude | Longitude | Location | Action Name | Description | Contact | Organisations Involved | Task Finish Group | Icon | IconColour
|  | Itchen Bank | STW Improvements | P Removal in AMP5 yr2 | Colin Sully | STW | LCP

## Suggested Actions
Latitude | Longitude | Location | Action Name | Description | Contact | Organisations Involved | Potential Funding Initiatives | Task Finish Group | Funding Applied For? | Funding Approved? | Actions | Icon | IconColour
|  | General | Creation of tree and woodland buffers | Adjacent to water bodies to reduce pollution, reduce sediment, nitrate, phosphate and pesticide concentrations and reduce water temperature to improve oxygen levels. | Justin Milward | Woodlands Trust, Forestry Commission | MOREwoods (Woodland Trust) | Habitats
|  | General | Creation of native woodland | On arable, improved pastrue and urban areas and as part of SUDS | Justin Milward | Woodlands Trust, Forestry Commission | MOREwoods (Woodland Trust) | Habitats
|  | Upland Headwaters | Resoration of PAWS (Planted Ancient Woodland Sites) | Broadleaf woodland and other semi-natural habitats to reduce nitrate concentrations and improve water quality. | Justin Milward | Woodlands Trust, Forestry Commission | MOREwoods (Woodland Trust) | Habitats
|  | General | Creation/restoration of floodplain woodland | Broadleaf woodland to slow the rate of flooding | Justin Milward | Woodlands Trust, Forestry Commission | MOREwoods (Woodland Trust) | Habitats
|  | Strategic Locations (report due out in new year) | Tree Planting | Warwick District Council Green Infrastructure |  |  | Match up with WDC GI initiative | Habitats |  |  | Contact Sam Todd to see if WDC report did come out in New Year Determine if any contact/matching up of resources has been carried out with WDC Hunt down WDC GI Initiative
|  | Leam, Itchen and Sowe | River Fencing | Fencing of reaches, including installation of troughs, watering bays and gates | Melissa Hoskings |  | Catchment Restoration Fund | Habitats | 29th Feb 2012
|  | Catchment Wide | Surfacing of muddy farm tracks | Muddy Farm Tracks to lay with hard chippings where appropriate | Melissa Hoskings |  | Catchment Restoration Fund | Habitats | 29th Feb 2012
|  | Leam and Itchen | Introduction of gravel to reaches | The introduction of gravel to increase flow diversity to improve aquatic invertebrate populations. | Melissa Hoskings |  | Catchment Restoration Fund | Habitats | 29th Feb 2012
|  | Confluence of Sowe and Itchen (eastern outskirts of Southam) | Wetland Creation |  | Melissa Hoskings |  | Catchment Restoration Fund | Habitats | 29th Feb 2012
|  | Catchment Wide | Low Phosphate Detergent Campaign | Promotion of low phosphate detergent for domestic use to reduce nutrient loading of watercourses | Colin Sully / Tim Pickering |  |  | LCP
|  | Catchment Wide | Fencing of fields where cattle poaching evident | Reduce access of cattle to watercourses to reduce siltation and phosphate loading. | Steve Foster (EA) |  |  | LCP
|  | Catchment Wide | Yellow Fish Campaign |  | Tim Haseldon (WWT) |  |  | LCP
|  | Catchment Wide | Sowe Valley Project | Extension of Sowe Valley Project to increase public awareness | Tim Haseldon (WWT)
|  | Catchment Wide | MURCI Waters extension |  | Colin Sully |  |  | LCP
|  | Catchment Wide | SUDS |  |  |  |  | Habitats
|  | Catchment Wide | Drainage Ditches |  |  |  |  | Habitats
|  | Catchment Wide | Flood Alleviation Schemes |  |  |  |  | Habitats
|  | Catchment Wide | Education of public | Publicise the problems in the catchment |  |  |  | Both
|  | Catchment Wide | Sharing of tenant farmer contacts |  | Matt Jeffes | Warwickshire County Council |  | Both
|  | Catchment Wide | Publicity of Pilot Project | Increase public awareness through farmers weekly, local NFU, stalls at agricultural events , Warwickshire College courses, VI texting list, free papers, hub, parish council newsletters |  |  |  | Both
|  | Catchment Wide | Tie into other communications | To increase general awareness in pilot |  |  |  | Both
|  | Stoneleigh area | Join forces with local horticulture groups |  |  |  |  | Both
|  | Catchment Wide | Cost Benefit Analysis of actions |  |  |  |  | Both
|  | Catchment Wide | Understand risk of actions |  |  |  |  | Both
|  | Catchment Wide | Understand timescales of actions |  |  |  |  | Both
|  | Catchment Wide | Timing and control of phosphate applications compared to nitrate regulation | Reduction in overapplication of phosphates to reduce nitrate loading of watercourses |  |  |  | LCP

## Completed Actions
Latitude | Longitude | Location | Action Name | Description | Contact | Organisations Involved | Delivery | Success? | Reason | Icon | IconColour
|  | Catchment wide | Pesticide Reduction | Voluntary work on pesticide reduction | Jo Kennedy (EA) | VI | 2011/12 | No | ?
|  | Midlands | Woodland for Water Phase 1 | Mapping of areas of Midlands where woodland planting can deliver WFD and Flood Risk benefits | Sam Todd | EA, Woodlands Trust, Consultants | 2011/12 | Get update from Colin
SP49756703, SP47196849, SP34306612, SP41166899, SP39966943, SP39306997, SP39106989 |  | River Leam | Bank Protection | Fencing and tree planting to reduce siltation and therefore nutrient and sediment transfer to watercourse | Colin Sully | EA, private landowners | 2011/12 | Get update from Colin
|  | Catchment wide | FWAG visits to sell Entry Level Stewardship | Aim to reduce nutrient loading of watercourse by increasing take up of ELS training | Colin Sully | EA, FWAG, Farmers | 2011/12 | Get update from Colin
|  | Catchment wide | Public Perception Survey | Finding out what is important to the public in order to facilitate engagement in reduction of nutrient loading | Claire Quigley | EA, public | 2011/12 | Get update from Colin or Claire
|  | Upstream of Campion Hills | Match Funding Project with STW | Partnership with STW to hold workshops to influence farmers, presticide suppliers, agronomists/farm consultants in how to best use pesticides and reduce environmental impact. Benefit for STW in reduction of pesticide treatment required at Campion Hills | Claire Quigley | EA, STW, public | 2011/12 | Get update from Colin or Claire
|  | ? | Passive Sampling | Identification of pesticides and locations of use | Colin Sully | EA | 2011/12 | Get update from Colin
|  | Eathorpe | Hydromorphic Audit | Investigation of impacts on weir removal on flood risk and system hydromorphology | Mike Adams (EA) | EA, JBA | 2011 | No | Weir removal is not a feasible option
|  | Catchment wide | Catchment Walkovers |  | Melissa Hoskings (SRT) / Colin Sully (EA)
|  | Catchment wide | Remote Sensing | LIDAR to determine vegetation cover |  | EA, STW |  | Check same as remote sensing data held by Colin

## Ongoing Actions
Latitude | Longitude | Location | Action Name | Description | Contact | Organisations Involved | Delivery | Funding | Actions | Icon | IconColour
|  | Catchment wide? | Safeguard Zone Action Plan | Protection of drinking water abstractions in the Leam from pesticide pollution | Jo Kennedy, Glyn Williams (EA) | EA, VI, STW
|  | Southam | Individual Property Protection | Individual property protection against flood risk | Luke Gaynham (EA) |  |  |  | Chase up with Luke
|  | ? | New ditches | New ditches as part of drainage schemes for flood mitigation and to create new habitats | Matt Jeffes (WCC) | WCC
|  | ? | Flood Alleviation Schemes | Provision of flood risk protection, combined with habitat improvements and silt removal where possible. | Matt Jeffes (WCC) | WCC, EA
|  |  | Nature Reserves | Continued operation |  | WWT
|  | Catchment wide? | Higher Level Stewardship Schemes
|  | Catchment wide? | Entry Level Stewardship Schemes
|  | Catchment wide? | Agrienvironmental schemes
|  | Eathorpe | Eathorpe Marsh |  |  | STW, WWT
|  | Catchment wide? | Mink Monitoring
|  | Catchment wide? | Invertebrate Monitoring
|  | Princethorpe Woodlands | Living Landscapes
|  | Catchment wide? | SUDS
|  | Catchment wide? | English Woodland Grant Scheme (EWGS) Projects
|  | Catchment wide? | SIMCAT Modelling | To identify the source of pollutants/phoshates
|  | Catchment wide? | Walkover surveys | To identify problems and pollution sources in the catchment
|  | Catchment wide? | Sampling | Check and review for ongoing evidence collection and improvement monitoring
|  | Catchment wide? | Infrastructure Improvements |  |  |  |  | Capital Grants
|  | Itchen Bank | Phosphate removal | Ongoing
|  | Catchment wide? | VI Investigations
|  | Catchment wide? | Watercourse Consenting
|  | Catchment wide? | Land Management, advice, regulations and grants | For private and other landowners |  | Forestry Commission
|  | Catchment wide? | National Environmental Programme of Catchment Scale Investigation |  |  | STW

## Barriers to Acheiving Aims
Source control of Phosphates entering the system
Loss of farming sales through reduction in fertilisers
Septic tanks
Translation of WFD requirements and costs to customers and requirement for ‘upstream thinking’